## Open decisions
India Australs 2027 — open decisions
Everything the website is holding a blank space for. Fill in Owner and By when, then work down the list.
Live list on the site: https://mahornagda.github.io/india-australs-2027/progress/
# | Area | What we need to decide | Why it matters | Owner | By when | Status
1 | Registration | Confirm 27 June to 4 July 2027 is final, and not moving
2 | Registration | Which countries and regions are eligible
3 | Registration | The cap on teams per university
4 | Registration | Whether a debater signs up for themselves, or their university signs up for its teams | This changes the shape of the registration form, so it is worth settling early
5 | Registration | The day registration opens and the day it closes
6 | Money | The entry fee, and exactly what it covers
7 | Money | Whether accommodation at The Grand sits inside the fee or on top of it
8 | Money | How people pay: card, bank transfer or UPI | This decides which payment company we sign up with
9 | Money | The scholarship route: who it is for, and what it covers
10 | Judging | How many judges a team must bring
11 | Judging | Whether independent adjudicator applications are capped, and how they are assessed
12 | Rounds | How many preliminary rounds, and how many motions go out in advance
13 | Rounds | The break structure: Open, ESL, EFL, and how many teams in each
14 | Rounds | The day-by-day running order
15 | Rounds | Whether the existing tab software stays, or is wired into this site
16 | Equity | Who sits on the equity team, and the confidential address to reach them
17 | Equity | The equity policy, written out in full
18 | Equity | The participant handbook, written out
19 | Logistics | How teams get between The Grand and campus each morning, and who pays for it
20 | Logistics | When we can issue visa invitation letters, and what they cover
21 | Logistics | A room-by-room access survey of the campus and the hotel | So we can say what is step-free instead of assuming
22 | Website | The email address the site should send from | Confirmation emails need an address that is ours and that will not land in spam
23 | Website | A web address of our own to put the site on | It sits on a free address today, which works but does not read as ours
24 | Website | How long we keep people's details after the tournament ends
25 | People | Surnames for Anjali and Kamal, our two senior advisors | Their posters only carry first names
26 | People | Debating records for the twenty-one advisors | The posters carry their names and countries and nothing else